PBIS Countdown to Kick-off!

|  |  |  |
| --- | --- | --- |
| 10 | Structures in Place | * PBIS Team is established & has regular meetings scheduled * Communication plan and feedback loops are developed between PBIS Team & staff |
| 9 | Introduction to PBIS | * PBIS Team creates plan to present Introduction to PBIS to staff * Introduction to PBIS is presented to staff |
| 8 | Staff Buy-In & Current Resources | * Compelling ‘why’ is developed * Staff commitment to PBIS is established (at least 80% of staff agree to this work) * School Climate Survey is completed * Resource mapping is completed |
| 7 | Identify & Define  School-wide Behavioral Expectations | * PBIS Team creates plan to deepen staff learning around having 3-5 school-wide behavioral expectations * PBIS Team & staff create 3-5 school-wide behavioral expectations * PBIS Team creates plan to deepen staff learning around defining school-wide expectations in all settings * PBIS Team develops behavior matrix/takes back to staff to approve |
| 6 | Prepare to Teach & Monitor Behavioral Expectations | * PBIS Team creates plan to deepen staff learning around teaching expectations * PBIS Team & staff create lesson plans for teaching expectations in each setting * PBIS Team & staff create a plan for teaching the lessons |

|  |  |  |
| --- | --- | --- |
| 5 | Positive & Corrective Feedback | * PBIS TEAM creates plan to deepen staff learning around acknowledgements * PBIS TEAM & staff develop a school-wide acknowledgement system * PBIS TEAM creates plan to deepen staff learning around correcting behavior * PBIS TEAM & staff develop a consistent response system for behavioral correction |
| 4 | Data Systems | * PBIS TEAM will complete the Tiered Fidelity Inventory (TFI) * PBIS TEAM & staff develop Office Discipline Referral form (ODR) * PBIS TEAM will work with their SWIS Facilitator to complete SWIS readiness requirements and obtain license |
| 3 | Finalize Development of All Components | * 3-5 Behavioral Expectations * Behavior matrix * Lesson plans for all settings * Plan for teaching the lessons * Plan for monitoring behavior * Acknowledgement system * Consistent behavioral response plan |
| 2 | Plan PBIS Kick-Off Assembly | * Date chosen * Who will do what |
| 1 | Order, create, gather all PBIS materials | * Create posters, visual displays, etc. * Acknowledgement system items * Include PBIS information in staff & student handbooks, parent newsletters |